## Webstore Launching Process
Webstore Launching Process
Customer: | Full Compass | Program # | FULL
Date: | 10/14/2022 | Customer # | 48048
Launch Date: | Nov 1, to close Nov15 to ship well before Christmas | UP/Down Lisa
$46 to each employee ( 200 emp)
7 items, one color offered, LC on all, BKPK done at starline
all orders picked up by Full Compass-no shipping costs
Task |  | Documents | Assigned To | Assigned Date | Done (w/Date)
Issue Store Notifications via email to Accounting, Manufacturing, Warehouse (shipping), Purchasing, Art and entire webstore team. Add dates to Electronic Webstore Calendar. |  |  | Webstore Service
Web Store Cust Svc Rep send email to Art Dept. for Banner and High Res Logo. Create Webstore Folder with images folder containing logo for Art Dept. to use |  | BANNER | Webstore Service | X | 2022-10-14
Once the Banner & High Res Image are complete, email Andy (give him PO # & fill in PO# worksheet) to create skin of store. Use informational sheet with needed information |  | M:\WEBSTORES\Andy Kulis Programming PO's.xlsx | Webstore Programmer
M:\WEBSTORES\FORMS\2.0 Prep.docx
Once Andy is done with skin, Four51 needs to be contacted to make the URL address
Web Cust Svc Rep & Sales work on Product Selection & Graphics - develop Exhibit A with pricing, royalties or rebates. |  |  | Webstore Service
If any items are embroidered - get stitch count quote from Embroidery Manager (Kourtney) |  |  | Webstore Service | X
Create the customer number and enter on Store Summary as well as Data page on this document. Ask Karlene to create program # when BOM's are created |  |  | BOM Creator | X | 2022-10-14
Web Cust Svc Rep develop Customer Agreement based on store type and include Royalty or Rebate, frequency of pymt, form of pymt and save in Customer Webstore folder |  |  | Webstore Service
Email agreement with royalties and rebate information to Jeff (cc Roger) along with list of items getting Royalty or Rebate from the "Store Summaries" for Approval BEFORE sending to customer |  |  | Webstore Service | NA
Once Exhibit A is approved & Graphics are finalized, Web Store Programmer submit art request for product & category images to Art Department |  | WEBSTORE ART REQUEST.xlsx | Webstore Service
Once Art proofs are complete, send to customer for approval. |  | Proof Approval | Webstore Service
Email Art Dept (and CC Kourtney if any are emb) with approval of proof sheets - Kourtney will send off to get digitized & Kim will send files out to appropriate depts (screen, digital, spec. dec., etc.). |  |  | Webstore Service | x | already on file
Once product images are completed, Web Cust Svc Rep notify Web Store Programmer |  | Four51 Programming | Webstore Programmer
Once Exhibit A is approved, Web Order Processor print the appropriate tabs of this document and meet with departments internally to verify program date schedule & share store details. Reps from Accounting, Manufacturing, Warehouse (shipping), Purchasing, and entire webstore team. Add process/ship dates to webstore calendar |  | This is the document | Webstore Operations
Web Cust Svc Rep submit Exhibit A to Item Master Programmer for BOM Creation (make sure she knows any royalties or rebates information!) CREATE program number and add to store summary |  | BOMs | Webstore Service
Order any stock items (hard goods, patches, transfers, stock apparel item, etc.). |  |  | Webstore Operations | NA
Once Exhibit A is approved, Web Order Processor begin work on Order Excel's and Warehouse Pick List & Alpha Product Registration |  | PICK LIST | Webstore Operations
If there are any specialty decorating items - email Spec. Dec. dept a copy of the proof sheet to show placement & let them know the patch item # so they know what they looking for. |  | USE PROOF SHEET | Webstore Service
Web Cust Svc Rep submit Agreement & Exhibit A to the Accounting Dept as well as the Sales Rep to get customer signature on contract |  |  | Webstore Service
Web Store Programmer program items to website with images, custom text, and finalize any additional programming necessary such as Shipping Addresses in Four51 and in Profitmaker(activate addresses so they appear online) Make sure spending A/C money appears on tool bar |  |  | Webstore Programmer
Live Site Review by Team before Turning Store On(Ck that tax is applied if needed, size charts work, color's change in drop down, ckout page works) |  | LIVE TEST | Webstore Team
Send link to Sales Rep to send to Customer & Add the store to the Sales person's Viewing list so they can see the orders |  |  | Webstore Service
Dates on Calender |  | DATES | Webstore Service
Order Processing Template |  | Process Template | Webstore Operations
After orders ship Web Cust Svc Rep follows up with Accounting on time frame and amount of Rebate/Royalty payment and emails customer with that information |  |  | Webstore Service

## Data
Details about the Customer
Customer Name:
Customer Number:
Sales Rep:
Customer Contact:
Phone:
E-mail:
Ever had a store before?
Expected Annual Sales?
Who will use the store?
How will the store be marketed?
Store Program #?
Programming
What color scheme for the skin of the store?
How will users access the store?
If Custom URL - what URL?
Store Password Protected? (Yes, if need to sign in before looking at the store; No if can roam the store and then log in when ordering)
Expected # of Store Users:
If users are mix of emp & cust, do they have different pricing?
Need any Groups?
If yes, Group Details?
Stock or On Demand Store?
If Mixed - do we split Ship Stock from On Demand products?
If split, how are we capturing enough $$$ to cover two shipments?
Store Timing
Time Span of Store
If Always Up - Store Launch Date?
If Always Up - Order Ship Frequency?
If by order, how long do we have to ship each order (in working days) for Stock products?
If by order, how long do we have to ship each order (in working days) for custom products?
If Bi-Monthly or Monthly, Process excels?
If Up/Down, # Cycles?
First Cycle Launch
First Cycle Close
First Cycle Production Complete
First Cycle Ship
Second Cycle Launch
Second Cycle Close
Second Cycle Production Complete
Second Cycle Ship
Payment Details
Are Sales Taxable? If So, What State?
Purchase Method @ Company Level
If Company Level Other - Details:
Purchase Method @ Group Level
If Group Level Other - Details:
Purchase Method @ Individual Level
Which Individuals get this?
If Individual Level Other - Details:
Any purchase funding Support? If yes, What?
Need Coupons/Spend Acct/Gift Cards?
Details of Coupon/SA/GC?
Rebate / Royalty to Customer?
If Yes, Flat Amt per item or percentage?
What is the Amt or Percentage?
Payable by Check or Credit Account
How Frequently paid?
Account AP Contact Name:
Account AP Contact Phone:
Account AP Contact E-mail:
Are invoices mailed or e-mailed?:
If E-mailed - E-mail address:
Products/Categories
Date for Item Selections to be complete?
How many items in the store?
What type of items?
How many colors per item (approx)?
Type of Decoration (@ Top only)
Are we offering Personalization on products?
If Yes, Personalization Details:
List Product Categories:
Can the customer return product?
BOM's Auto Produced?
Show inventory on Four51?
Any info in extended description (besides blank item # & garment color (plus garment code)?
Order Processing
Excel Order Forms, Order Processing Template, or use system paperwork?
If system paperwork - ASI or Four51?
Packing/Shipping
How are orders being packaged
If Bulk, Shipped to where? & How?
If Individual Ship or Pick-Up?
If Ship, Ship Method
If Ship Method Other, Details:
If Pick-Up - Pick Up from Where?
How are back orders being handled
BO- If Bulk, Shipped to where? & How?
BO- If Individual Ship or Pick-Up?
BO- If Ship, Ship Method
BO- If Ship Method Other, Details:
BO- If Pick-Up - Pick Up from Where?

## Store Fulfillment & Shipping
Details about the Customer
Customer Name: | 0
Customer Number: | 0
Sales Rep: | 0
Customer Contact: | 0
Stock or On Demand Store? | 0
If Mixed - do we split Ship Stock from On Demand products? | 0
If split, how are we capturing enough $$$ to cover two shipments? | 0
Store Timing
Time Span of Store | 0
If Always Up - Store Launch Date? | 0
If Always Up - Order Ship Frequency? | 0
If by order, how long do we have to ship each order (in working days) for Stock products? | 0
If by order, how long do we have to ship each order (in working days) for custom products? | 0
If Bi-Monthly or Monthly, Process excels? | 0
If Up/Down, # Cycles? | 0
First Cycle Launch | 0
First Cycle Close | 0
First Cycle Production Complete | 0
First Cycle Ship | 0
Second Cycle Launch | 0
Second Cycle Close | 0
Second Cycle Production Complete | 0
Products/Categories
How many items in the store? | 0
What type of items? | 0
Type of Decoration (@ Top only) | 0
Are we offering Personalization on products? | 0
If Yes, Personalization Details: | 0
Packing/Shipping
How are orders being packaged | 0
If Bulk, Shipped to where? & How? | 0
If Individual Ship or Pick-Up? | 0
If Ship, Ship Method | 0
If Ship Method Other, Details: | 0
If Pick-Up - Pick Up from Where? | 0
How are back orders being handled | 0
BO- If Bulk, Shipped to where? & How? | 0
BO- If Individual Ship or Pick-Up? | 0
BO- If Ship, Ship Method | 0
BO- If Ship Method Other, Details: | 0
BO- If Pick-Up - Pick Up from Where? | 0

## Item Setup & BOM's
Details about the Customer
Customer Name: | 0
Customer Number: | 0
Sales Rep: | 0
Customer Contact: | 0
Phone: | 0
E-mail: | 0
Store Timing
Time Span of Store | 0
If Always Up - Store Launch Date? | 0
If Up/Down, # Cycles? | 0
First Cycle Launch | 0
Products/Categories
Date for Item Selections to be complete? | 0
How many items in the store? | 0
What type of items? | 0
How many colors per item (approx)? | 0
Type of Decoration (@ Top only) | 0
Are we offering Personalization on products? | 0
If Yes, Personalization Details: | 0
List Product Categories: | #REF!
Can the customer return product? | 0
BOM's Auto Produced? | 0
Show inventory on Four51? | 0
Any info in extended description (besides blank item # & garment color (plus garment code)? | 0

## Accounting
Details about the Customer
Customer Name: | 0
Customer Number: | 0
Sales Rep: | 0
Customer Contact: | 0
Phone: | 0
E-mail: | 0
Store Timing
Time Span of Store | 0
If Always Up - Store Launch Date? | 0
If Always Up - Order Ship Frequency? | 0
If Up/Down, # Cycles? | 0
First Cycle Launch | 0
First Cycle Ship | 0
Second Cycle Launch | 0
Second Cycle Ship | 0
Payment Details
Are Sales Taxable? If So, What State? | 0
Any purchase funding Support? If yes, What? | 0
Need Coupons/Spend Acct/Gift Cards? | 0
Details of Coupon/SA/GC? | 0
Rebate / Royalty to Customer? | 0
If Yes, Flat Amt per item or percentage? | 0
What is the Amt or Percentage? | 0
Payable by Check or Credit Account | 0
How Frequently paid? | 0
Accounting Details
Account AP Contact Name: | 0
Account AP Contact Phone: | 0
Account AP Contact E-mail: | 0
Are invoices mailed or e-mailed?: | 0
If E-mailed - E-mail address: | 0

## Programming
Programming
What color scheme for the skin of the store? | 0
How will users access the store? | 0
If Custom URL - what URL? | #REF!
Store Password Protected? | 0
Expected # of Store Users: | 0
If users are mix of emp & cust, do they have different pricing? | 0
Need any Groups? | 0
If yes, Group Details? | 0
Stock or On Demand Store? | 0
If Mixed - do we split Ship Stock from On Demand products? | 0
If split, how are we capturing enough $$$ to cover two shipments? | 0